## Slide 1
UTM ROLLOUT
MARKET STATUS AND CONFIRMED GREEN LIGHTS
Only explicitly confirmed green lights are marked as green. Silence is treated as not yet confirmed.
11
Markets engaged
1
Resolved
7
In progress
3
No response / blocked
Current read
France is the only market with explicit platform green lights in the source note: Google and Meta.

## Slide 2
MARKET STATUS: AUSTRALIA TO FRANCE
Client ask answered with explicit platform confirmation only
MARKET
GREEN LIGHT
STATUS
KEY POINT
NEXT STEP
Australia
None confirmed yet
IN PROGRESS
UTM mismatches between GA4 and 1R; placements missing
Fix UTMs and resolve access gaps by 21 Apr
Portugal
None confirmed yet
NO RESPONSE
DV360 missing from GA4 and 1R; market has not replied
Escalate and secure response before deadline
UK
None confirmed yet
IN PROGRESS
Amazon and Always-on not in Planit; AV team builder issue
Fix non-Hive campaigns and confirm compliance
MENA
Scoped out correctly
RESOLVED
No active PME campaigns
Monitor only; use new builder when live
South Korea
None confirmed yet
BLOCKED
Ingestion feasibility unconfirmed; validation not possible yet
Market response and ingestion check required
France
Google, Meta
IN PROGRESS
Platforms implemented; March validation still pending
Run March extract and close if aligned

## Slide 3
MARKET STATUS: SWITZERLAND TO LATAM
Client ask answered with explicit platform confirmation only
MARKET
GREEN LIGHT
STATUS
KEY POINT
NEXT STEP
Switzerland
None confirmed yet
IN PROGRESS
Placement IDs reused across multiple UTMs
Restore 1:1 UTM-to-placement mapping
Poland
None confirmed yet
IN PROGRESS
Missing placement IDs; Social still on old UTMs
Clarify retrofit policy and move April live
Norway
None confirmed yet
NEEDS SETUP
No Planit schematic for Always On
Full setup required from scratch
PCEE
None confirmed yet
IN PROGRESS
Package-level UTMs used instead of placement-level
Complete remapping across affected markets
LATAM
None confirmed yet
CLARIFYING
DV360 routed via CM360 autotagging
Align tracking approach before validation