## Sheet1
Market | Step 1 – Global (You) | Step 1 – Market Response | Step 2 – Global (Chloe) | Step 2 – Market Response | Step 3 – Global | Next Action (Us) | Next Action (Market) | Step 3 - Global
Australia (PCA) | Asked for UTM adoption check: flagged 1 campaign missing + only DV360 Audio visible in GA4; requested validation vs Planit + fix UTMs (deadline 27 Mar) | Acknowledged, but challenged visibility: say multiple channels live (YT, BVOD, Display, Audio); ask what “outstanding campaign” + GA4 audio refers to | Shared detailed audit: mismatches GA4 vs 1R (placements missing / old UTMs / access gaps), highlighted COOP + SEM issues, suggested causes | — (no direct response after detailed audit yet) | Minor coordination (sharing campaign info, housekeeping) | 1) Answer their clarification (which campaign + GA4 audio)2) Translate audit into actionable list per placement (not just diagnosis)3) Push closure vs deadline | 1) Investigate mismatches vs Planit2) Fix UTMs (new builder)3) Resolve GA4 ↔ 1R gaps (tracking or access)4) Confirm full channel visibility | Nudge/Deadline 21April EOD
Portugal () | Always‑on Search and DV360 activity are not consistently visible in GA4; DV360 is also missing from One.Reporting. Next steps are to validate DV360 account and campaign IDs for Portugal and ensure account mappings are aligned between GA4 and One.Reporting. | NO Response yet | NUDGE SENT, DEADLINE 21 APRIL EOD
UK (PCGB) | Flagged issues: low Planit coverage vs live campaigns, non-compliant UTMs (e.g. Amazon), misalignment Planit vs execution; requested clarification + fix UTMs | Acknowledged, looped in planning team; committed to investigate as priority | — | Detailed response: campaigns briefed via Hive (should use new UTMs), identified gaps (Amazon, Always-on not in Planit, UK biddable team not following Hive), AV team issue with UTM builder; committing to fix urgently | — | 1) Support AV team on UTM builder issue2) Validate their fixes actually resolve GA4/Planit gaps3) Push for confirmation once compliant | 1) Fix non-Hive / non-Planit campaigns (Always-on, Amazon)2) Ensure full UTM compliance across all campaigns3) Resolve AV builder issue4) Align Planit with full live activity5) Confirm completion | Asked for the follow-up update by 21April
MENA (PME) | Asked to confirm UTM adoption; noted no tacticals currently planned; asked if any UTM activity expected | Confirmed no PME brand activity live or planned (last ended Feb); aligned to use new UTM builder for any future activity; noted dealer activity exists (outside PME scope) | — | — | — | 1) Confirm scope exclusion (dealer activity vs PME)2) Monitor for any new PME campaigns | 1) Ensure future PME campaigns use new UTM builder2) Flag when new activity is planned
South Korea | Validation on our end currently not possible. Confirm ingestion feasibility before assessing UTM compliance. | NO Response yet
France (POF) | Flagged major gaps: only 1 campaign compliant, Search & Social not updated, Planit duplication/inconsistencies; asked to fix UTMs + Planit | Strong pushback: claim all UTMs updated via new builder; say Planit is up to date; ask which campaigns/issues identified | Shared audit (Jan/Feb): clear mismatches (1R vs GA4), multiple placements live without UTMs (Search + Social), some missing/not found |  | NUDGE SENT/Deadline 21April EOD | 1) Point to exact campaigns/placements (from audit) to break disagreement2) Confirm if updates happened post-Feb audit3) Push for validation proof (GA4 + Planit alignment) | 1) Validate audit discrepancies vs current setup2) Fix any remaining UTM mismatches3) Ensure Planit clean (no duplication)4) Confirm full compliance with evidence
Switzerland (PCH) | Flagged issue: placements live in 1R but not resolving in GA4 → UTM recognition problem; asked to investigate tagging consistency | Responded that UTMs created via new builder; only 2 campaigns live; GA shows traffic; asked to recheck | Chloe identified mismatch: same Planit IDs used across multiple UTMs; 10 IDs in 1R not found in UTM data; suggests duplication / incorrect usage | Explained root cause: 1 placement ID reused across multiple sitelinks → multiple UTMs per ID; confirms structure issue | Ongoing discussion via call | 1) Clarify expected 1:1 mapping (Placement ID ↔ UTM)2) Confirm if multi-UTM per ID breaks GA4 ingestion3) Provide fix guidance (structure, not just symptoms) | 1) Fix UTM structure (avoid multiple UTMs per placement ID)2) Align sitelink usage with UTM logic3) Ensure GA4 can resolve all placements4) Confirm corrected setup post-call
Poland (PPL) | Flagged issues: missing placement IDs (Search, YouTube, Demand Gen), Social without new UTMs, no GA4 visibility; asked to rebuild UTMs + validate | Asked if update is required given campaign ends end of March (legacy Q4 extension); understood new UTMs apply only from April campaigns | — | Added trafficking team to discussion (alignment step, no resolution yet) | — | 1) Clarify policy: whether ongoing campaigns must be retrofitted vs only new ones2) Confirm minimum requirement before campaign end (if any) | 1) Align on UTM rollout timing (current vs new campaigns)2) Apply new UTMs for all April campaigns3) Ensure placement IDs + GA4 visibility for new setup
Norway (PNO) | Flagged: Search & Social visible in 1R but not using new UTMs; no GA4 visibility; asked to update UTMs + validate | Asked for help: no Planit setup (no schematic/tacticals), needs support for Always-On + UTM builder | Chloe looped in Planit team (Sam, Beth) | Sam identified root cause: no schematic/tacticals exist → nothing set up in Planit | Ongoing coordination | 1) Support full setup (Planit + UTM builder) via Planit team2) Define required structure clearly (schematic → tactical → UTM)3) Shift from audit to onboarding support | 1) Create schematic + tactical setup in Planit2) Implement UTMs via builder3) Ensure GA4 ingestion4) Align with Planit team for correct setup
PCEE | Flagged: DV360 tagged but incomplete coverage; asked to confirm all campaigns use new UTMs | Internal delegation: asked HUB team to validate UTM updates across campaigns | — | Identified root cause: package-level UTMs used instead of placement-level → incomplete coverage; plan to fix via Artbot remapping across 23 markets | — | 1) Support Artbot mapping if needed2) Validate post-fix coverage (placement-level completeness)3) Ensure consistency across all markets | 1) Rebuild UTMs at placement-level via Artbot2) Roll out fix across all 23 markets3) Confirm full coverage and GA4 alignment
LATAM (CL) | Flagged: YouTube, DV360, Direct not appearing in GA4; asked to investigate tagging + account connections | Claimed UTMs implemented since March; internal check requested to validate correctness | — | Suggested alternative tracking: DV360 data coming via CM360 autotagging; questioning if GA4 source expectation differs; proposes alignment discussion | — | 1) Clarify required data source (GA4 vs CM360)2) Confirm expected tracking logic (UTM vs autotagging)3) Provide clear validation criteria | 1) Validate GA4 ingestion vs CM360 data2) Ensure UTMs correctly applied despite autotagging3) Align tracking approach with global standard4) Confirm visibility in GA4