## Logic Tracker
Ticket ID | Dimension / Field | Value / Logic Area | Issue Type | Current Problem | Proposed Logic / Rule | Channel Scope | Current-State or Future-State | Priority | Owner | Development Stage | Status | Dependencies / Risks | Stakeholder Input Needed | Dashboard Implementation Notes
TX-001 | Buying Platform | Channel = Paid Search | Irrelevant cross-channel usage | Search channel should not expose social, DSP, or direct-buy platforms. | Allowed values filter: allow Google Ads; Microsoft Ads; Bing; search-approved engines only | Paid Search | Current-State | High |  | Ready for Spec | Open | Needs confirmation that PlanIT can enforce this validation pattern. | Channel lead / taxonomy owner | Mirror the same rule in dashboard quality checks and filter logic.
TX-002 | Match Type | Channel = Paid Search | Missing controlled vocabulary | Search-specific concept; should be hidden elsewhere. | Field visibility condition: allow ALL; Exact; Broad; Phrase; Dynamic Search Ads | Paid Search | Current-State | High |  | Ready for Spec | Open | Needs confirmation that PlanIT can enforce this validation pattern. | Channel lead / taxonomy owner | Mirror the same rule in dashboard quality checks and filter logic.
TX-003 | Match Type | Channel = != Paid Search | Irrelevant cross-channel usage | Current workbook shows search concepts leaking into non-search rows. | Forbidden-if condition: allow NULL only | Multi-channel | Current-State | High |  | Ready for Spec | Open | Needs confirmation that PlanIT can enforce this validation pattern. | Channel lead / taxonomy owner | Mirror the same rule in dashboard quality checks and filter logic.
TX-004 | Keyword Type / Messaging | Channel = != Paid Search | Irrelevant cross-channel usage | Keyword messaging is search-only and placeholder states should not be used elsewhere. | Forbidden-if condition: allow NULL only | Multi-channel | Current-State | High |  | Ready for Spec | Open | Needs confirmation that PlanIT can enforce this validation pattern. | Channel lead / taxonomy owner | Mirror the same rule in dashboard quality checks and filter logic.
TX-005 | Buying Platform | Channel = Paid Social | Irrelevant cross-channel usage | Social should not present search or direct-buy platform lists. | Allowed values filter: allow Facebook Business Manager; LinkedIn Ads; Pinterest Ads; Reddit Ads; TikTok; social-approved platforms | Paid Social | Current-State | High |  | Ready for Spec | Open | Needs confirmation that PlanIT can enforce this validation pattern. | Channel lead / taxonomy owner | Mirror the same rule in dashboard quality checks and filter logic.
TX-006 | Buying Platform | Channel = Display / iVideo / Connected TV (CTV) | Irrelevant cross-channel usage | Programmatic and direct inventory require a different platform vocabulary. | Allowed values filter: allow Google - DV360; The Trade Desk; Amazon DSP; Direct Buy; channel-specific approved vendors | Display / iVideo / Connected TV (CTV) | Current-State | Medium |  | Ready for Spec | Open | Needs confirmation that PlanIT can enforce this validation pattern. | Channel lead / taxonomy owner | Mirror the same rule in dashboard quality checks and filter logic.
TX-007 | Buying Mode | Buying Platform = Direct Buy | Missing controlled vocabulary | Programmatic open inventory mode is not meaningful for direct-buy rows. | Field visibility condition: allow NULL or direct-buy specific value only | Direct Buy | Current-State | Medium |  | Ready for Spec | Open | Needs confirmation that PlanIT can enforce this validation pattern. | Channel lead / taxonomy owner | Mirror the same rule in dashboard quality checks and filter logic.
TX-008 | Format / Dimensions | Channel = Paid Search | Irrelevant cross-channel usage | Search rows currently contain placeholder format constructs rather than meaningful search values. | Allowed values filter: allow Search-specific values only; no generic display sizes | Paid Search | Current-State | Medium |  | Ready for Spec | Open | Needs confirmation that PlanIT can enforce this validation pattern. | Channel lead / taxonomy owner | Mirror the same rule in dashboard quality checks and filter logic.
TX-009 | Buying Mode | Sub Channel = Programmatic - Display / Video / Audio | Missing controlled vocabulary | Trading mode matters only in applicable programmatic contexts. | Mandatory-if condition: allow Programmatic Open Inventory and other approved programmatic modes | Programmatic - Display / Video / Audio | Current-State | Medium |  | Ready for Spec | Open | Needs confirmation that PlanIT can enforce this validation pattern. | Channel lead / taxonomy owner | Mirror the same rule in dashboard quality checks and filter logic.
TX-010 | KPI Objective | Planning Principle = Awareness | Irrelevant cross-channel usage | Funnel principle should constrain valid KPI choices. | Allowed values filter: allow Awareness; Video Views; Reach-type objectives | Awareness | Current-State | Medium |  | Ready for Spec | Open | Needs confirmation that PlanIT can enforce this validation pattern. | Channel lead / taxonomy owner | Mirror the same rule in dashboard quality checks and filter logic.
TX-011 | Cross-field governance | Remove placeholder values such as Mixed, Not Used, Other, Unknown and blanks from input dropdowns wherever possible. | Missing controlled vocabulary | These values dominate several fields and are degrading governance immediately. | Remove placeholder values such as Mixed, Not Used, Other, Unknown and blanks from input dropdowns wherever possible. | All | Current-State | 1 |  | Backlog | Open | May affect templates, reporting and PlanIT dropdown configuration. | Taxonomy owner / analytics owner | Translate into specific dashboard rules or warnings once finalised.
TX-012 | Cross-field governance | Make Match Type and Keyword Type / Messaging search-only conditional fields. | Missing controlled vocabulary | They are currently leaking into non-search rows and creating invalid taxonomy states. | Make Match Type and Keyword Type / Messaging search-only conditional fields. | All | Current-State | 2 |  | Backlog | Open | May affect templates, reporting and PlanIT dropdown configuration. | Taxonomy owner / analytics owner | Translate into specific dashboard rules or warnings once finalised.
TX-013 | Cross-field governance | Restrict Buying Platform by Channel and Sub Channel. | Missing controlled vocabulary | Platform dropdowns should be channel-aware to stop invalid combinations at source. | Restrict Buying Platform by Channel and Sub Channel. | All | Current-State | 3 |  | Backlog | Open | May affect templates, reporting and PlanIT dropdown configuration. | Taxonomy owner / analytics owner | Translate into specific dashboard rules or warnings once finalised.
TX-014 | Cross-field governance | Convert Format Mix and Dimensions Mix into reporting-only derived states. | Missing controlled vocabulary | These are aggregation outputs masquerading as input choices. | Convert Format Mix and Dimensions Mix into reporting-only derived states. | All | Current-State | 4 |  | Backlog | Open | May affect templates, reporting and PlanIT dropdown configuration. | Taxonomy owner / analytics owner | Translate into specific dashboard rules or warnings once finalised.
TX-015 | Cross-field governance | Split Targeting into source and method, or at minimum tighten allowed values by channel. | Missing controlled vocabulary | Current values mix audience source, targeting method and operational workarounds. | Split Targeting into source and method, or at minimum tighten allowed values by channel. | All | Current-State | 5 |  | Backlog | Open | May affect templates, reporting and PlanIT dropdown configuration. | Taxonomy owner / analytics owner | Translate into specific dashboard rules or warnings once finalised.
TX-016 | Cross-field governance | Review Supplier and Vendor for consolidation into a single governed entity field. | Missing controlled vocabulary | Duplication increases maintenance and inconsistency risk. | Review Supplier and Vendor for consolidation into a single governed entity field. | All | Current-State | 6 |  | Backlog | Open | May affect templates, reporting and PlanIT dropdown configuration. | Taxonomy owner / analytics owner | Translate into specific dashboard rules or warnings once finalised.
TX-017 | Structural redesign | Redesign taxonomy by channel family rather than forcing one globally generic set of dropdowns. | Design smell workaround | Search, Social and Programmatic require different governed concepts. | Redesign taxonomy by channel family rather than forcing one globally generic set of dropdowns. | All | Future-State | 1 |  | Backlog | Open | Likely requires template and historical compatibility review. | Chloe / Sam Tait / channel leads | Not for immediate dashboard implementation; keep visible for roadmap planning.
TX-018 | Structural redesign | Replace Local Channel TACT workaround structures with proper object-level taxonomy and string-generation logic. | Design smell workaround | Fields containing 'String Only' are design smells, not business taxonomy. | Replace Local Channel TACT workaround structures with proper object-level taxonomy and string-generation logic. | All | Future-State | 2 |  | Backlog | Open | Likely requires template and historical compatibility review. | Chloe / Sam Tait / channel leads | Not for immediate dashboard implementation; keep visible for roadmap planning.
TX-019 | Structural redesign | Introduce a normalized funnel-stage model separate from campaign planning and reporting objectives. | Design smell workaround | Current fields partially duplicate and conflict with each other. | Introduce a normalized funnel-stage model separate from campaign planning and reporting objectives. | All | Future-State | 3 |  | Backlog | Open | Likely requires template and historical compatibility review. | Chloe / Sam Tait / channel leads | Not for immediate dashboard implementation; keep visible for roadmap planning.
TX-020 | Structural redesign | Move message strategy, audience source and targeting method into separately governed dimensions. | Design smell workaround | Current field overload limits analytical usability. | Move message strategy, audience source and targeting method into separately governed dimensions. | All | Future-State | 4 |  | Backlog | Open | Likely requires template and historical compatibility review. | Chloe / Sam Tait / channel leads | Not for immediate dashboard implementation; keep visible for roadmap planning.
TX-021 | Audience Source / Data Source | Missing dimension | Missing dimension | Current Targeting and Audience Segment fields mix source and tactic in one place. | Add dimension with example values: Tealium; CRM; Pixel retargeting; Platform native interest; 2P; 3P; Contextual | Social, Programmatic, Display, Video | Current-State feasible | High |  | Backlog | Open | Needs agreement on field ownership, level, and allowed values. | Laura / Chloe / analytics / channel owners | Add as new controlled field or derived dashboard dimension depending on implementation route.
TX-022 | Targeting Method | Missing dimension | Missing dimension | Targeting field currently bundles incompatible concepts. | Add dimension with example values: Interest; In-market; Retargeting; Keyword; Contextual; Lookalike; Demographic | Search, Social, Programmatic, Display | Current-State feasible | High |  | Backlog | Open | Needs agreement on field ownership, level, and allowed values. | Laura / Chloe / analytics / channel owners | Add as new controlled field or derived dashboard dimension depending on implementation route.
TX-023 | Funnel Stage | Missing dimension | Missing dimension | Planning Principle values are too numerous and partially overlapping. | Add dimension with example values: Awareness; Consideration; Conversion | All | Future-State | High |  | Backlog | Open | Needs agreement on field ownership, level, and allowed values. | Laura / Chloe / analytics / channel owners | Add as new controlled field or derived dashboard dimension depending on implementation route.
TX-024 | Creative / Message Family | Missing dimension | Missing dimension | Keyword Type / Messaging is search-biased and cannot serve all channels. | Add dimension with example values: Brand; Model; Offer; Aftersales; Launch; Tactical | All paid media | Future-State | High |  | Backlog | Open | Needs agreement on field ownership, level, and allowed values. | Laura / Chloe / analytics / channel owners | Add as new controlled field or derived dashboard dimension depending on implementation route.
TX-025 | Inventory Logic | Missing dimension | Missing dimension | Buying Mode is too narrow and mostly filled with placeholders. | Add dimension with example values: Open Exchange; PMP; PG; Direct IO; Retail sponsored | Programmatic, Display, CTV, Retail media | Current-State feasible | High |  | Backlog | Open | Needs agreement on field ownership, level, and allowed values. | Laura / Chloe / analytics / channel owners | Add as new controlled field or derived dashboard dimension depending on implementation route.

## Guide
How to use
1. Add one row per logic issue, rule, missing field, or governance ticket.
2. Use dropdowns for Issue Type, Channel Scope, Current-State or Future-State, Priority, Development Stage, and Status.
3. Keep Proposed Logic / Rule specific enough to implement in the dashboard or PlanIT validation layer.
4. Use Dashboard Implementation Notes to describe how the logic should surface in the app.
Suggested workflow
Backlog -> To Review -> Ready for Spec -> Ready for Build -> In Development -> In UAT -> Done

## Lists (hidden)
Too many values | All | Current-State | Critical | Backlog | Open
Irrelevant cross-channel usage | Search | Future-State | High | To Review | In Progress
Redundant with another field | Social |  | Medium | Ready for Spec | Waiting for Input
Ambiguous naming | Programmatic |  | Low | Ready for Build | Blocked
Free-text risk | Display |  |  | In Development | Closed
Low usage but important | CTV |  |  | In UAT
Placeholder / bad fallback value | Video |  |  | Blocked
Missing controlled vocabulary | Inventory Ads |  |  | Done
Missing dimension | Direct Buy
Wrong granularity | Multi-channel
Reporting-only value used as input
Design smell workaround