## Instructions
UTM Market Response Form
Market: PCGB
Source file: Porsche_UTM Adoption Feedback_March26_UPDATED_with_Owner_and_Blockers.xlsx
How to fill this file (simple and complete):
1) Open 'Issue Responses': each row is an issue from the central input file for your market. | Important:
2) Do NOT edit input columns (A-F). Fill only response columns (G-P). | Input columns in Issue Responses are prefilled from central review.
3) Use dropdown values whenever available (traffic light, status, support needed, confidence). | Please avoid editing input columns; respond in response columns.
4) If Response Traffic Light is Amber/Red, provide clear action plan and target date. | Use Action Log for additional tasks and blockers.
5) Use 'Action Log' for detailed follow-up actions that need tracking over time.
6) Save and return this file with the same structure (do not rename sheets/columns).
Traffic Light meaning:
Green = fully healthy / no urgent action
Amber = partially healthy / action required soon
Red = blocked / urgent support required
Not Live = channel not active
Unknown = no confirmed evidence yet

## Issue Responses
Market | Platform (from input) | Input Traffic Light | Input Status Notes | Input Key Point | Input Next Step | Response Traffic Light | Response Status | Response Summary | Response Action Plan | Support Needed From Central | Response Owner Name | Response Owner Email | Response Target Date | Last Updated | Confidence
PCGB | Amazon | Other concept implemented | 4 Amazon placements found in 1R but not in GA4 data - live with different concept? UK to confirm status | Activity using alternative/legacy UTM concept. Present in One.Reporting but missing (or non-compliant) in GA4. | Confirm current UTM logic in use, migrate to the new structure, and validate with GA4 + One.Reporting.
PCGB | DV360 | Other concept implemented | Can see DV360 data in GA4 with different concept implemened for Porschealwayson and Macan Bev - UK to confirm status | Activity using alternative/legacy UTM concept. Can see DV360 data in GA4 with different concept implemened for Porschealwayson and Macan Bev - UK to confirm status | Confirm current UTM logic in use, migrate to the new structure, and validate with GA4 + One.Reporting.
PCGB | Google Ads | Partial implementation | Compliant UTMs found for all search except: All Planit placement IDs in PLANIT begin with '2012'. All placement IDs in 1R begin with '2028' - manipulation of IDs happening outside of planit. Need to confirm how utms have been created? Concern IDs wont match. No compliant UTMs found for: Macan ICE - PMAX 911 - VLA Panamera - VLA Macan BEV - VLA Taycan - VLA | Partial adoption of new UTM structure. Planit Placement IDs differ between Planit and One.Reporting (risk of broken joins/compliance). | Market to complete UTM remediation for missing placements/campaigns and re-check across Planit, GA4 and One.Reporting.
PCGB | Microsoft | Other concept implemented | PMAX campaigns not found in GA4 dataset or One.Reporting. All Planit placement IDs in PLANIT begin with '2012'. All placement IDs in 1R begin with '2028' - manipulation of IDs happening outside of planit. Need to confirm how utms have been created? Concern IDs wont match. Cayenne campaigns not in planit but found in One.Reporting - IDs made up outside of planit? | Activity using alternative/legacy UTM concept. Planit Placement IDs differ between Planit and One.Reporting (risk of broken joins/compliance). | Align with DTO Planit + Compliance teams on correct object mapping (package vs placement) and migrate trafficking to the new UTM structure.
PCGB | Linkedin | Partial implementation | 3 Linkedin Campaigns live in 1R but not new UTMs found - UK to confirm | Partial adoption of new UTM structure. 3 Linkedin Campaigns live in 1R but not new UTMs found - UK to confirm | Market to complete UTM remediation for missing placements/campaigns and re-check across Planit, GA4 and One.Reporting.

## Action Log
Channel | Priority | Action Description | Blocker Type | Owner | Due Date | Status | Dependency | Notes

## Lists (hidden)
Traffic Light | Implementation Status | Data Quality | Tracking Quality | Blocker Type | Yes/No | Confidence | Priority | Action Status | Channels | Response Status
Green | Fully implemented | Good | Reliable | No blocker | Yes | High | Critical | Open | Google Ads | Reviewed
Amber | Partially implemented | Needs review | Some issues | Tracking setup | No | Medium | High | In progress | Google Inventory Ads | In progress
Red | In progress | Poor | Major gaps | Tagging consistency |  | Low | Medium | Blocked | Bing | Blocked
Not Live | Not started | No data | Unknown | Naming/taxonomy |  |  | Low | Done | Facebook | Resolved
Unknown | Not applicable |  |  | Platform configuration |  |  |  |  | Facebook Inventory Ads | Not applicable
|  |  |  | Agency process |  |  |  |  | Tiktok
|  |  |  | Client approval |  |  |  |  | LinkedIn
|  |  |  | Data pipeline |  |  |  |  | Pinterest
|  |  |  | Other |  |  |  |  | DV360
Amazon
Direct Buys