## Instructions
UTM Market Response Form
Market: PCEE
Source file: Porsche_UTM Adoption Feedback_March26_UPDATED_with_Owner_and_Blockers.xlsx
How to fill this file (simple and complete):
1) Open 'Issue Responses': each row is an issue from the central input file for your market. | Important:
2) Do NOT edit input columns (A-F). Fill only response columns (G-P). | Input columns in Issue Responses are prefilled from central review.
3) Use dropdown values whenever available (traffic light, status, support needed, confidence). | Please avoid editing input columns; respond in response columns.
4) If Response Traffic Light is Amber/Red, provide clear action plan and target date. | Keep responses concise but complete so central review can consolidate easily.
5) Keep one clear response per issue row with owner, target date, and summary.
6) Save and return this file with the same structure (do not rename sheets/columns).
Traffic Light meaning:
Green = fully healthy / no urgent action
Amber = partially healthy / action required soon
Red = blocked / urgent support required
Not Live = channel not active
Unknown = no confirmed evidence yet

## Issue Responses
Market | Platform (from input) | Input Traffic Light | Input Status Notes | Input Key Point | Input Next Step | Response Traffic Light | Response Status | Response Summary | Response Action Plan | Support Needed From Central | Response Owner Name | Response Owner Email | Response Target Date | Last Updated | Confidence
PCEE | DV360 | Partial implementation | check placement strings in planit - looks like market = cee, when it should equal individual countries. Countries defined in freetext instead. | Partial adoption of new UTM structure. check placement strings in planit - looks like market = cee, when it should equal individual countries. Countries defined in freetext instead. | Check with Planit and Compliance teams | Amber | In progress | Placement strings currently use CEE instead of individual countires. New UTM structure is only partially adopted. | We are reviewing the placement strings set up in Planit and aligning with the correct country level structure. Updates will be implemented accordingly. | Yes | Aneta Cihlová Líbalová | aneta.cihlova@omc.com | Mid-May 2026 | 2026-04-28 | Medium

## Lists (hidden)
Traffic Light | Implementation Status | Data Quality | Tracking Quality | Blocker Type | Yes/No | Confidence | Priority | Action Status | Channels | Response Status
Green | Fully implemented | Good | Reliable | No blocker | Yes | High | Critical | Open | Google Ads | Reviewed
Amber | Partially implemented | Needs review | Some issues | Tracking setup | No | Medium | High | In progress | Google Inventory Ads | In progress
Red | In progress | Poor | Major gaps | Tagging consistency |  | Low | Medium | Blocked | Bing | Blocked
Not Live | Not started | No data | Unknown | Naming/taxonomy |  |  | Low | Done | Facebook | Resolved
Unknown | Not applicable |  |  | Platform configuration |  |  |  |  | Facebook Inventory Ads | Not applicable
|  |  |  | Agency process |  |  |  |  | Tiktok
|  |  |  | Client approval |  |  |  |  | LinkedIn
|  |  |  | Data pipeline |  |  |  |  | Pinterest
|  |  |  | Other |  |  |  |  | DV360
Amazon
Direct Buys