## Instructions
UTM Market Response Form
Market: PD
Source file: Porsche_UTM Adoption Feedback_March26_UPDATED_with_Owner_and_Blockers.xlsx
How to fill this file (simple and complete):
1) Open 'Issue Responses': each row is an issue from the central input file for your market. | Important:
2) Do NOT edit input columns (A-F). Fill only response columns (G-P). | Input columns in Issue Responses are prefilled from central review.
3) Use dropdown values whenever available (traffic light, status, support needed, confidence). | Please avoid editing input columns; respond in response columns.
4) If Response Traffic Light is Amber/Red, provide clear action plan and target date. | Keep responses concise but complete so central review can consolidate easily.
5) Keep one clear response per issue row with owner, target date, and summary.
6) Save and return this file with the same structure (do not rename sheets/columns).
Traffic Light meaning:
Green = fully healthy / no urgent action
Amber = partially healthy / action required soon
Red = blocked / urgent support required
Not Live = channel not active
Unknown = no confirmed evidence yet

## Issue Responses
Market | Platform (from input) | Input Traffic Light | Input Status Notes | Input Key Point | Input Next Step | Response Traffic Light | Response Status | Response Summary | Response Action Plan | Support Needed From Central | Response Owner Name | Response Owner Email | Response Target Date | Last Updated | Confidence
PD | Meta | Partial implementation | MetaInventoryAds2026NWTaycan (campaign id - 20293375) - not live? Looks like only 911 is live. | Partial adoption of new UTM structure. MetaInventoryAds2026NWTaycan (campaign id - 20293375) - not live? Looks like only 911 is live. | Market to complete UTM remediation for missing placements/campaigns and re-check across Planit, GA4 and One.Reporting. | Green | Reviewed | Taycan is live. UTM have been implemented in the tracking portion of the set up: utm_campaign=cid%3A20293375_ca%3Ametainventoryads2026nwtaycan&utm_id=pc%3A%ebuy!%7Cpp%3A%epid!&utm_content=pn%3A20294167%7Ecn%3Ataycan+lal%7Emo%3ATAY_TAY%7Eco%3ADE%7Eln%3ADE%7Ecta%3Alearnmore%7Eaid%3A%ecid!%7Epo%3A41357917 |  | No
PD | DV360 | Partial implementation | AOProgrammaticPerformance2026 (campaign id - 20130912) using new utm but not found in 1R - check ad account | Partial adoption of new UTM structure. AOProgrammaticPerformance2026 (campaign id - 20130912) using new utm but not found in 1R - check ad account | Market to complete UTM remediation for missing placements/campaigns and re-check across Planit, GA4 and One.Reporting. | Amber | Not applicable | UTM confirmed to be in use. DV360 Data visibilaty is general an issue in 1R. Annalect needs to check.
PD | Google Ads | Partial implementation | SEA National 2026 (campaing id - 20056448), some campaigns live with new UTM. Confirm if others not live or live with alternative. Can share specific campaigns if asked. Check planit start date for Cayenne E4 Family (campaign id - 20205848) and Taycan Sales Push 2026 (campaign id -20176562) - not found in GA4 or 1R Demand Gen Campaign - Panamera Sales Push 2026 (campaign id - 20173475)- partial use of new utm but no data in 1R. Check status of campaigns. | Partial adoption of new UTM structure. SEA National 2026 (campaing id - 20056448), some campaigns live with new UTM. Confirm if others not live or live with alternative. Can share specific campaigns if asked. Check plan… | Market to remediate missing/mismatched UTMs (ensure Planit placement IDs carried through), then re-check GA4 + One.Reporting with 2–3 sample IDs. | Red | In progress | SEA BAH collegues are still in discussions with Keith Wong & Team regarding most efficient implementation approach. | Implementation will take place asap
PD | Linkedin | Hypothesis - no active campaigns | Check start date for MacanDienstwagenpush2026 (campaign id -20172604) - Planit suggests some activity should be live | No clear evidence of live activity / tracking. Check start date for MacanDienstwagenpush2026 (campaign id -20172604) - Planit suggests some activity should be live | Market/hub to confirm whether activity is live and share ad account/library details. If live, validate compliant UTMs and data ingestion into GA4 + One.Reporting. | Green | Reviewed | Campaign starts in July

## Lists (hidden)
Traffic Light | Implementation Status | Data Quality | Tracking Quality | Blocker Type | Yes/No | Confidence | Priority | Action Status | Channels | Response Status
Green | Fully implemented | Good | Reliable | No blocker | Yes | High | Critical | Open | Google Ads | Reviewed
Amber | Partially implemented | Needs review | Some issues | Tracking setup | No | Medium | High | In progress | Google Inventory Ads | In progress
Red | In progress | Poor | Major gaps | Tagging consistency |  | Low | Medium | Blocked | Bing | Blocked
Not Live | Not started | No data | Unknown | Naming/taxonomy |  |  | Low | Done | Facebook | Resolved
Unknown | Not applicable |  |  | Platform configuration |  |  |  |  | Facebook Inventory Ads | Not applicable
|  |  |  | Agency process |  |  |  |  | Tiktok
|  |  |  | Client approval |  |  |  |  | LinkedIn
|  |  |  | Data pipeline |  |  |  |  | Pinterest
|  |  |  | Other |  |  |  |  | DV360
Amazon
Direct Buys