## Instructions
UTM Market Response Form
Market: PLA
Source file: Porsche_UTM Adoption Feedback_March26_UPDATED_with_Owner_and_Blockers.xlsx
How to fill this file (simple and complete):
1) Open 'Issue Responses': each row is an issue from the central input file for your market. | Important:
2) Do NOT edit input columns (A-F). Fill only response columns (G-P). | Input columns in Issue Responses are prefilled from central review.
3) Use dropdown values whenever available (traffic light, status, support needed, confidence). | Please avoid editing input columns; respond in response columns.
4) If Response Traffic Light is Amber/Red, provide clear action plan and target date. | Keep responses concise but complete so central review can consolidate easily.
5) Keep one clear response per issue row with owner, target date, and summary.
6) Save and return this file with the same structure (do not rename sheets/columns).
Traffic Light meaning:
Green = fully healthy / no urgent action
Amber = partially healthy / action required soon
Red = blocked / urgent support required
Not Live = channel not active
Unknown = no confirmed evidence yet

## Issue Responses
Market | Platform (from input) | Input Traffic Light | Input Status Notes | Input Key Point | Input Next Step | Response Traffic Light | Response Status | Response Summary | Response Action Plan | Support Needed From Central | Response Owner Name | Response Owner Email | Response Target Date | Last Updated | Confidence
PLA | Meta | Partial implementation | Handful of placements live in 1R but not found in GA4 data for the below campaigns (can follow up with exact details) PLACayenneBEQ12026 PLAMetaTestLeadAds PLAQ1NewsletterCreditFB PLATINS2026 | Partial adoption of new UTM structure. Handful of placements live in 1R but not found in GA4 data for the below campaigns (can follow up with exact details) PLACayenneBEQ12026 PLAMetaTestLeadAds PLAQ1NewsletterCreditFB … | Market to complete UTM remediation for missing placements/campaigns and re-check across Planit, GA4 and One.Reporting. | Red | In progress | all the UTMs are now following the last process (using plan it & then the excel document), Direct, DV360 and social are using the same process. Looking to connect with global team to take a look into the mistakes |  | Yes | Daniela Castro | Daniela.castro@omc.com | May 8th |  | High
PLA | Direct | Partial implementation | 2 x direct placements found in 1R but not in Ga4 data - other utm concept implemented (Usmedia) | Partial adoption of new UTM structure. Present in One.Reporting but missing (or non-compliant) in GA4. | Market to complete UTM remediation for missing placements/campaigns and re-check across Planit, GA4 and One.Reporting. | Red | In progress | all the UTMs are now following the last process (using plan it & then the excel document), Direct, DV360 and social are using the same process. Looking to connect with global team to take a look into the mistakes |  | Yes | Erika Garcia | erika.garcia@omc.com | May 8th |  | Medium
PLA | DV360 | Full Implementation | UTMs updated | New UTM structure implemented. UTMs updated | No immediate action required; continue monitoring and re-validate in the next monthly check. | Green | Not applicable
PLA | Youtube | Full Implementation | UTMs updated | New UTM structure implemented. UTMs updated | No immediate action required; continue monitoring and re-validate in the next monthly check. | Green | Not applicable
PLA | Direct | Other concept implemented | Placement found in 1R but not found in | Activity using alternative/legacy UTM concept. Placement found in 1R but not found in | Confirm current UTM logic in use, migrate to the new structure, and validate with GA4 + One.Reporting. | Amber | In progress | all the UTMs are now following the last process (using plan it & then the excel document), Direct, DV360 and social are using the same process. Looking to connect with global team to take a look into the mistakes |  | Yes | Erika Garcia | erika.garcia@omc.com | May 8th |  | Medium

## Lists (hidden)
Traffic Light | Implementation Status | Data Quality | Tracking Quality | Blocker Type | Yes/No | Confidence | Priority | Action Status | Channels | Response Status
Green | Fully implemented | Good | Reliable | No blocker | Yes | High | Critical | Open | Google Ads | Reviewed
Amber | Partially implemented | Needs review | Some issues | Tracking setup | No | Medium | High | In progress | Google Inventory Ads | In progress
Red | In progress | Poor | Major gaps | Tagging consistency |  | Low | Medium | Blocked | Bing | Blocked
Not Live | Not started | No data | Unknown | Naming/taxonomy |  |  | Low | Done | Facebook | Resolved
Unknown | Not applicable |  |  | Platform configuration |  |  |  |  | Facebook Inventory Ads | Not applicable
|  |  |  | Agency process |  |  |  |  | Tiktok
|  |  |  | Client approval |  |  |  |  | LinkedIn
|  |  |  | Data pipeline |  |  |  |  | Pinterest
|  |  |  | Other |  |  |  |  | DV360
Amazon
Direct Buys