## Instructions
UTM Market Response Form
Market: PSG
Source file: Porsche_UTM Adoption Feedback_March26_UPDATED_with_Owner_and_Blockers.xlsx
How to fill this file (simple and complete):
1) Open 'Issue Responses': each row is an issue from the central input file for your market. | Important:
2) Do NOT edit input columns (A-F). Fill only response columns (G-P). | Input columns in Issue Responses are prefilled from central review.
3) Use dropdown values whenever available (traffic light, status, support needed, confidence). | Please avoid editing input columns; respond in response columns.
4) If Response Traffic Light is Amber/Red, provide clear action plan and target date. | Keep responses concise but complete so central review can consolidate easily.
5) Keep one clear response per issue row with owner, target date, and summary.
6) Save and return this file with the same structure (do not rename sheets/columns).
Traffic Light meaning:
Green = fully healthy / no urgent action
Amber = partially healthy / action required soon
Red = blocked / urgent support required
Not Live = channel not active
Unknown = no confirmed evidence yet

## Issue Responses
Market | Platform (from input) | Input Traffic Light | Input Status Notes | Input Key Point | Input Next Step | Response Traffic Light | Response Status | Response Summary | Response Action Plan | Support Needed From Central | Response Owner Name | Response Owner Email | Response Target Date | Last Updated | Confidence
PSG | Meta | Partial implementation | PSGR26001 SG CNY Campaign - planit end date is February but onsite data found in GA4 report for March. 1 placement with compliant UTM - planit placement ID is 20130037 For PSGR26003 Cayenne Black Edition, one planit placement ID found in GA4 data (finished on 30th March according to planit) (Planit placement id - 20124919) | Partial adoption of new UTM structure. PSGR26001 SG CNY Campaign - planit end date is February but onsite data found in GA4 report for March. 1 placement with compliant UTM - planit placement ID is 20130037 For PSGR2600… | Market to complete UTM remediation for missing placements/campaigns and re-check across Planit, GA4 and One.Reporting. | Not Live | Reviewed | Campaigns are fully completed, any rectifications to UTMs will not be reflected. Kindly advise next step. |  | Yes | Christy/ Thara
PSG | Direct | Other concept implemented | Campaign found in 1R but no IDs found in GA4 data | Activity using alternative/legacy UTM concept. Campaign found in 1R but no IDs found in GA4 data | Check implementation status | Unknown | Reviewed | What channel does Direct refer to here? There are several Direct channels that PSG utilises - Offline and Digital. |  | Yes | Christy/ Thara
PSG | Teads | Other concept implemented | Campaign found in 1R but no IDs found in GA4 data | Activity using alternative/legacy UTM concept. Campaign found in 1R but no IDs found in GA4 data | Check implementation status | Unknown | Reviewed | Which campaigns are using the old UTMs? Is this for the Cayenne Black campaign? |  | Yes | Christy/ Thara

## Lists (hidden)
Traffic Light | Implementation Status | Data Quality | Tracking Quality | Blocker Type | Yes/No | Confidence | Priority | Action Status | Channels | Response Status
Green | Fully implemented | Good | Reliable | No blocker | Yes | High | Critical | Open | Google Ads | Reviewed
Amber | Partially implemented | Needs review | Some issues | Tracking setup | No | Medium | High | In progress | Google Inventory Ads | In progress
Red | In progress | Poor | Major gaps | Tagging consistency |  | Low | Medium | Blocked | Bing | Blocked
Not Live | Not started | No data | Unknown | Naming/taxonomy |  |  | Low | Done | Facebook | Resolved
Unknown | Not applicable |  |  | Platform configuration |  |  |  |  | Facebook Inventory Ads | Not applicable
|  |  |  | Agency process |  |  |  |  | Tiktok
|  |  |  | Client approval |  |  |  |  | LinkedIn
|  |  |  | Data pipeline |  |  |  |  | Pinterest
|  |  |  | Other |  |  |  |  | DV360
Amazon
Direct Buys